27 April 2016

MEMORANDUM

SUBJECT:		THOMPSON EDUCATION CENTER

WELL PERMIT

On this date, a meeting was held at Town Hall to discuss the Permit Application for well drilling for subject project.  Representing the Applicant John Privitera, Attorney, Tom Decker, Contractor, representing the Town Paula Kay, Jim Carnell, Dick McGoey and Bob Geneslaw on the phone.  The Applicant was requested to meet in a work session to discuss issuance of the Well Permit.  The Applicant had received a notification from the Town denying the permit originally.  The following was discussed:

- The flagging for the wetlands is no longer existent or visible in the field.  The Applicant is proposing to have the Surveyor stay ahead of the well drilling rig and flag the wetlands.  We requested that the Applicant submit a plan showing the Phases in which the wells will be drilled and the flagging will be performed.

- Bob Geneslaw recommended that in light of the wetlands delineation is over a year old, that the Applicant check with NYSDEC to determine if a re-delineation will be required and also suggested that he discuss the wetland map and the age of the wetland delineation with Pietrzak and Pfau, their present Consultant for advice.  The original wetland maps were prepared by JL Consulting, surveyed by Joseph Haller dated 12/14/06.

3.	The Applicant will be providing the Town with approvals from the adjoining property owners to gain access to the existing Well No. 5 which does not show a road on the map.  In addition, the maps will be revised to show the existing and/or proposed access road into Well No. 5 as well as the names of the property owners.

- McGoey, Hauser and Edsall, to review the well monitoring plan which was submitted to the Town.  We questioned the ability of the Applicant to limit the width of the disturbance for the access roads as noted in the SWPPP plan to 12’.  We requested that they confirm this with their Engineer and make a modification to the width of

disturbance in the SWPPP plan, if necessary.

4.	The Town requested that a letter be received from the Fire and Ambulance 	Service that a 12’ access road is satisfactory for access, otherwise modifications 	will be required.

5.	We understand from Pietrzak and Pfau that a Notice of Intent has been issued 	from NYSDEC; however, the Town is to review the SWPPP plan before proceeding.

6.	The Applicant’s Engineer is to submit a Restoration Bond to restore the site if in fact that project does not proceed including restoration of the roadways constructed, restoration of the well sites and their disturbance.  This estimate is to be submitted to the Town for review and acceptance and a Bond posted prior to issuance of a Permit to proceed to prepare the well sites.